## Gear Parameters
gear name | type of gear | Connection to preceding gear |  | Pitch Diameter (mm), D | Module (mm/tooth), m | Number of Teeth, z
|  | Type | Name
A | Spur | N/A | N/A | 10 | 1 | 10
B | Spur | mesh | A | 20 | 1 | 20
C | Spur | axial | B | 10 | 1 | 10
D | Spur | mesh | C | 20 | 1 | 20
E | Spur | axial | D | 10 | 1 | 10
F | Spur | mesh | E | 18 | 1 | 18

## Gantt Chart
Task | Start Date | End Date | Duration
Milestone 0 | 2020-02-07 | 2020-02-14 | 7
Hand-drawn Sketches & Calculation | 2020-02-14 | 2020-02-24 | 10
Documentation of Milestone 1 | 2020-02-24 | 2020-02-28 | 4
Group Meeting | 2020-02-28 | 2020-02-29 | 1
Solid Modelling & Print Gears | 2020-02-28 | 2020-03-08 | 9
Group Meeting | 2020-03-08 | 2020-03-09 | 1
Print and Assembly | 2020-03-08 | 2020-03-30 | 22
Documentation of Milestone 2 | 2020-03-08 | 2020-03-13 | 5
File Submissions and Interview | 2020-03-30 | 2020-04-07 | 8
Peer Evaluation | 2020-04-01 | 2020-04-08 | 7